## Sheet1
Issue # | Task Title/User stories | Story Points | Due Dates | Task Description | Priority | Risk | Risk explanation | Responsible
1 | README file | 1 | 2024-09-29 | Create and complete the repository's README File | High | Low | Would be crazy to break something with this | Haichuan, Jeffrey
2 | User can enter username and password to log in | 4 | 2024-09-29 | Create Welcome page. Create login page, add log in window to fill log in informations. Create account database. Link frontend and backend | High | Medium | Databse being manipulated, but not high risk as this is the first step of development, so nothing to break | Haichuan, Jeffrey
3 | User can create teams and assign students to specific groups | 4 | 2024-09-29 | Build functionality for users to create teams and assign students to groups. | High | Medium | Database being manipulated | Jeremie, Ayman
4 | Users should be visible to see teams | 2 | 2024-09-29 | Implement team visibility feature for users to view all teams and their members. | High | Medium | Database being manipulated | Jeremie, Ayman
5 | Users should be able to choose from Instructor or Student Login | 1 | 2024-09-29 | Create buttons for seperate logins. Create pages for seperate logins. | High | Low | No data is being modified | Varun, Francois
6 | User can create password when creating an account | 2 | 2024-09-29 | Create page for first time logins to create password. | High | Medium | Password creation might lock out users if forgotten password or typo | Varun, Francois
7 | User can logout | 1 | 2024-09-29 | Create logout button | Medium | Low | Simply a button to redirect | Varun, Francois
8 | User can change password | 2 | 2024-09-29 | Create button and page to change user password. | Low | High | Potential to ruin password fields | Varun, Francois
9 | User can click on another student's name to bring the user to that student's profile | 2 | 2024-09-29 | Add a direct link that brings the user to a student profile: | Low | Low | Redirection link | Jeremie, Ayman
10 | Automatic Student Team Assignment | 3 | 2024-09-30 | Develop feature for CSV upload and student profile creation: - Create a CSV upload form for instructors. - Parse CSV and extract student data. - Implement student profile creation in the database. - Handle errors for malformed files. - Update database schema for student profiles. - Test the CSV upload and profile creation process. | High | Medium | Potential file format issues with CSV upload | Haichuan, Francois
11 | Manual Student Team Assignment | 5 | 2024-10-02 | Design the team assignment UI. Implement drag-and-drop for assigning students to teams. Build backend to update team assignments. Provide real-time team updates. Validate and prevent duplicate team assignments. Test the team assignment functionality. | Medium | High | Complex logic for team assignment, prone to bugs | Haichuan, Francois
12 | View All Teams Dashboard | 4 | 2024-10-04 | Design and implement the team dashboard UI. Add filtering/sorting functionality. Build backend service to fetch and display teams. Implement pagination for large teams. Test team display and filtering. | High | Low | Minimal risk; mainly UI design | Haichuan, Francois
13 | Reassign Students Between Teams | 3 | 2024-10-06 | Add drag-and-drop or dropdown for reassigning students. Build backend logic to update team assignments. Ensure database integrity during reassignment. Implement real-time updates for reassigned students. Test the reassignment functionality. | Medium | Medium | Possibility of incorrect reassignment logic | Haichuan, Francois
14 | Download Team Assignments | 2 | 2024-10-08 | Add a "Download CSV" button. Implement backend service to generate a CSV file. Ensure proper CSV formatting and validation. Provide error handling for download issues. Test the CSV download process. | Low | Low | Straightforward implementation | Haichuan, Francois
15 | Instructors can see teams' submissions |  |  | Display team submissions in the instructor dashboard for review. | High | High
16 | Instructors can see students' individual grades |  |  | Provide individual grade visibility for each student in the instructor dashboard | High | Medium
17 | Students can see their grades |  |  | Implement student grade view functionality on the student dashboard. | Low | Low
| Intructors can see teams' peer reviews |  |  | Show peer review summaries for each team in the instructor dashboard. | Low | Low
| Students can see the reviews written about them |  |  | Show peer review summaries for each team in the instructor dashboard. | High | High
| As a user, we can get notified when there is a grade updated |  |  | Allow students to access and view peer reviews of themselves. | Medium | Low